## Project
ENGR 128 Studio - Task Tracking
| Project: | Digital Logic Circuit |  |  | Revision No: | 1 | Date: | 2020-02-27
# | Task Title | Task Explanation | Deliverable Item | Primary Person | Priority (A, B, C) |  | Task Dates |  |  | Days |  |  |  | Priority |  | Comments
[6 empty] | Assigned | Due | Received | Active? | Left | ≤ 1 Week | Overdue | Priority | Factor | Code
1 | Model F | Logic.ly circuit for output F | Model | Barnes | A | 2020-02-26 | 2020-02-27 |  | TRUE | 0 | TRUE | FALSE | A | 2 | 3
2 | Model K | Logic.ly circuit for output K | Model | Moor | A | 2020-02-26 | 2020-02-27 | 2020-02-27 | FALSE | 0 | TRUE | FALSE | B | 2 | 0
3 | Model M | Logic.ly circuit for output M | Model | Chen | A | 2020-02-26 | 2020-02-27 | 2020-02-26 | FALSE | 0 | TRUE | FALSE | C | 2 | 0
4 | Model P | Logic.ly circuit for output P | Model | Saha | A | 2020-02-26 | 2020-02-27 | 2020-02-26 | FALSE | 0 | TRUE | FALSE |  | 2 | 0
5 | Model integration | Combination of all circuits | Model | Moor | A | 2020-02-26 | 2020-02-28 |  | TRUE | 1 | TRUE | FALSE |  | 2 | 3 | Waiting on #1
6 | Test plan | Write test plan to evaluate model | Word document | Saha | B | 2020-02-26 | 2020-02-28 |  | TRUE | 1 | TRUE | FALSE |  | 1 | 2
7 | Model testing | Execute test plan | Test results | Chen | B | 2020-02-27 | 2020-03-02 |  | TRUE | 4 | TRUE | FALSE |  | 1 | 2
8 | Test assessment | Evaluate requirements | Email | Chen | C | 2020-02-27 | 2020-03-02 |  | TRUE | 4 | TRUE | FALSE |  | 0 | 1 | Email to #10 and #12
9 | Next steps | Determine design improvements | Email |  | C |  | 2020-03-02 |  | TRUE | 4 | TRUE | FALSE |  | 0 | 1 | Email to #10 and #12
10 | Oral presentation |  | PowerPoint | Barnes | A | 2020-02-27 | 2020-03-03 |  | TRUE | 5 | TRUE | FALSE |  | 2 | 3
11 | Subsystem integration | Combination of all groups | Model | Moor | C | 2020-02-27 | 2020-03-18 |  | TRUE | 20 | FALSE | FALSE |  | 0 | 0 | Done in Studio
12 | Technical report |  | Word document | Saha | B | 2020-02-27 | 2020-03-17 |  | TRUE | 19 | FALSE | FALSE |  | 1 | 1
13 | [8 empty] | FALSE | -43888 | TRUE | TRUE |  | 0 | 0
14 | [8 empty] | FALSE | -43888 | TRUE | TRUE |  | 0 | 0
15 | [8 empty] | FALSE | -43888 | TRUE | TRUE |  | 0 | 0
16 | [8 empty] | FALSE | -43888 | TRUE | TRUE |  | 0 | 0
| Rows will change format colors based on the priority and the due date. |  |  | Priority limited to A, B, or C: | [11 empty] | Tasks breakdown the major parts
| • Red background and bold when urgent. |  |  | • A - necessary work, need ASAP, at least by due date | [11 empty] | of the schedule into smaller pieces.
| • Yellow background when soon. |  |  | • B - necessary work, need by due date | [11 empty] | Each group member should have
| • Green background when not immediate. |  |  | • C - useful but not necessary work (yet), do as time permits | [11 empty] | active deliverables.